## Ez Prs Status
Updates
S.no | Ez Prs | Owner | ETA | Comments from
1 | Need to get wsdl for each asset for testing | Mallikarjun | TBD
2 | get the performance test scripts for Ezprs | Kurmanath | TBD | Need to discuss with HPE team Lilian[09/03]: Updated that, they don’t have cross Assets related cases. 10/03[Anantha]: Need to get the scripts from HPE to HPI environment. 10/03[Manjula]:Need to work with HPE team regarding Performance Testing. 13/03[Kurmanath]: Recieved script from HPE for EzPrs Performance related and uploaded in Share point. 13/03[AI]: Execution of Performance Test cases in HPE ITG asap. 14/03: Lilian updated scripts are not performance but it is sample Automation used by UFT and requested for valid Ezprs Scripts to Ranjan again. 17/03: ran the script for 50 Users and generated the Report.
3 | Get the details [ Test cases] of the cross Assets | Kurmanath | 2017-03-10 | Need to discuss with HPE team. 10/03:Need to setup a call with sandeep-chetan.yeruva@hp.com and manjula and Zhang, Zhi-Ou <zhiou.zhang@hp.com> - PRS QA Lead Mallikarjun is optional 10/03:: Cross Asset related price procedure & Assert Specific for data to find , need to create two supparate docs for easyness. 17/03: need to talk with chetan regard to Test data.
4 | Performance testing toll need to be confirmed | Manjula | 2017-03-09 | Installed LoadRunner in Local machine. 10/03: Need to get the update from Harish & Vijaya kumar from HPE Team. 13/03: Confirming the Tool will be done by 15/03.
5 | Upload test cases to TFS | Kurmanath | TBD

## Cross Assets
S.No | Cross Assets | Req for HPI
1 | orion
2 | omih
3 | fusion_e
4 | fusion_a
5 | fusion
6 | watson
7 | eclipse
8 | pdapi
9 | eco
10 | myprs
11 | smartquote
12 | ppc
13 | rosa
14 | recat
15 | inventory
16 | webaqs
17 | ganmon
18 | ippitg
19 | prs4xl
20 | dsl
21 | gsebp
22 | kenobi
23 | Below is a full list of all the ezPRS Clients:
24 | myPRS US Resellers
25 | LA ezStore
26 | LA eClaim
27 | OMIH (EU)
28 | EMS (US)
29 | IPCS/CQC
30 | PO (US)
31 | PPC (US)
32 | TSG
33 | Fusion
34 | Monitoring [Ganmon]

## My Prs Status
| My Prs | Owner | ETA | Comments | Status
1 | Test Data Identification and Test Case Update based on the data identified. | Narayanan | 2017-09-03 | 09/03:: Claraification update need to receive from HPE team and call setup has been done for 10/03 around 3 PM. 13/03: Out of 5 questions 3 questions are closed from Vijay & Team
2 | Complete cleanup of test cases | Narayanan | 13/03/2017 | Deffered
3 | Test case preparation for Home page , Reports and Help | Narayanan | 17/03/2017 | 10/03: Need to gothrough recordings & with HPE Team & previliged users availability need to check.
4 | Review & Rework
6 | Test Cases Upload to TFS | Narayanan
7 | Performance testing for My PRS | Narayanan | TBD | 10/03: Need to get the performance testcases for MY Prs .

## My Prs Questions
Query Details
Clarification # | Questions | Raised By | Raised On Date | Comments | Status
1 | Products should appear based on the Region or Owner or Country? | Narayanan | 2017-03-09 | 10/3: Region (Confirmed by Vijay from HPE team ) 20/3:Based on the user & region its appear - In myPRS admin tool we can able to control the region (Srinivasa) | Closed
2 | Any Difference in the menu or product display based on Region? | Narayanan | 2017-03-14 | 20/3: No (Only the product will differ) - Srinivasa | Closed
3 | How to test with various Region - Login details (How to change the region for a user and test the functionality) | Narayanan | 2017-03-09 | 10/3:From Mallikarjun: Ports not enable - no idea when will it up - load balance we cant test in dev enviroment. 20/3: What are the roles in myPRS - Normal( Control Access) & Super User(All) - Srinivasa How to assign different roles to a user https://myprs.hp.com/myprs/admin | Closed
4 | Context Components is not appearing in our test ITG Url | Narayanan | 2017-03-14 | 20/3:Role based or in General (No Idea - Srnivasa )--- Need to check with sekoya | Open
5 | How to cross verify the products appearing in the site with the actual - What are all the attribute we have to cross verify with PRS/GPSy | Narayanan | 2017-03-09 | 10/3:From Mallikarjun: Since HPI not doing unit testing so they are not aware of this… 20/3:We need to discuss with Chetan - What are all the attributes we have to cross verify with PRS 22/3: Chetan: No need to verify for values, just need to check the product is appearing or not | Closed
6 | What is the difference between Product Details and Analysis | Narayanan | 2017-03-09 | 17/3:Product details and Analyasis page asks to enter the same values but the output getting populated in both the pages are different. Analysis page populates some additional details as key/value pair columns. (From Amit 17/03) 20/3: (No Idea - Srnivasa )--- Need to check with sekoya | Open
7 | How to create a report template | Narayanan | 2017-03-09 | 17/3:You have to first load the basket with some SKUs and then will have to search the details after entering the proper values in the dropdown boxes available on the page.(From Amit 17/03) 20/3: Clarified by Srinivasa | Closed
8 | What we have to mention in Price List Box | Narayanan | 2017-03-14 | 20/3:We need to discuss with Chetan/Sekoya - Any Values we have to mention here | Closed
9 | Pricing Model: Offer Pricing, Deal Pricing, Context Pricing, Deal & Agrement are missing in in our test ITG Url - its in the User Guide | Narayanan | 2017-03-14 | 20/3:We need to discuss with Chetan/Sekoya 22/3: Chetan will provide the data | Open
10 | What is the usage of Bundle Pricing - Not mention in User Guide | Narayanan | 2017-03-14 | 20/3:We need to discuss with Chetan/Sekoya | Open